|  | TOPIC | ACTION TO BE TAKEN | PERSON IN CHARGE | STATUS |
| --- | --- | --- | --- | --- |
| 1 | Dates of the workshop | New Dates: April 26-27-28, 2006 FZ has to send an e-mail | Frank Zimmermannn | Confirmed. |
| 2 | Conference rooms | AB Auditorium booked by MM. MM to book the 6-2-002 MM to book the 6-2-008 | Muriel Macchi | Confirmed. |
| 3 | Local Organizing Committee | Site Web to be updated POSIPOL 2006 – Member list to be updated | Carlos Pinto-Pereira | In progress |
| 4 | International Program Committee Members | FZ+LR are going to make suggestions to the invitees. Who is given the talk; The topic of the talk. | Frank Zimmermann Louis Rinolfi | Tbc. |
| 5 | Program for the topics and numbers of sessions | Louis to contact people to get topics for editing the Agenda; To discuss and start working on agenda MCG works on the Agenda | Louis Rinolfi GG + LR + FZ Marie-Christine Guirao | In progress In progress In progress |
| 6 | Program of the visits (CLIC, CTF3, LHC, …) | Atlas visit on Thursday -14:00-16:00 – max 12 people; meeting point 13:45 – Bat.39. To be organized by MCG CLIC; CTF3; LHC, visits to be organized by LR – Visit – 16:00 – 18:00 | Marie-Christine Guirao Louis Rinolfi | In progress In progress |
| 7 | Web Pages | To be discussed with CPP, FZ, LR | Carlos Pinto-Pereira | In progress |
| 8 | Logo of the Workshop | FZ to check with Japan Emphasize on Positrons and Posipol. Wants to do a logo more specific. | FZ + GG + LR + CP | In progress |
| 9 | List of delegates participating to the Workshop | List generated by Indico MCG to check with CPP | Marie-Christine Guirao | Tbc. |
| 10 | Hotel Booking | 50 rooms have been booked with CERN HOSTEL. MM ask for 1 extra night; 25 people – check-out April 29 instead MM ask for price | Muriel Macchi | Waiting on seo. Answer |

|  | TOPIC | ACTION TO BE TAKEN | PERSON IN CHARGE | STATUS |
| --- | --- | --- | --- | --- |
| 11 | Contact for all travel matters | Contact to be communicated to participants: Marie-Christine Guirao Muriel Macchi | Louis Rinolfi to inform participants | Tbc. |
| 12 | Budget | Budget code: 60711 (EU-CERN-ELAN) MCG to submit a budget by next Thursday | Gilbert Guiganrd - Marie-Christine Guirao | Confirmed In progress |
| 13 | Intendance for Coffee breaks | Budget code: 60711 (EU-CERN-ELAN) MCG take care of it and ask for vouchers | Marie-Christine Guirao | Tbc. |
| 14 | Organization of the Dinner | Date: Thursday, April 27, 2006 Time: 19:30 Venue: tbc | Marie-Christine Guirao Muriel Macchi | Tbc. |
| 15 | Photography of the Workshop Attendees | Contact Maximilien Brice | Muriel Macchi | Tbc. |
| 16 | Proceedings of the Workshop | Committee has to ask participants to do a presentation, and then a written summary after the workshop is over. | Louis Rinolfi Frank Zimmermann | OK |
| 17 | Invitation’s letters | MM to write Invitation Letter and W.P. MM to check with Helene Haller which country needs to apply for a visa; FZ to communicate participants list to MM | Muriel Macchi Muriel Macchi Frank Zimmermann | In progress. Waiting done |
| 18 | Badges - Security | MCH will take care of issuing the badges - MCH will hand over a list to the guards | Marie-Christine Guirao | Tbc. |
| 19 | Welcome | Building 33; MCG to check with Mr. Bertolaz - MCH will hand over a list to the guards | Marie-Christine Guirao | OK |
| 20 | Shuttle | To be organized by MCG | Marie Christine Guirao | Tbc. |
| 21 | Welcome Drink | - Date: Wednesday, April 26, 2006 - To be organized by MCG | - Marie-Christine guirao | Tbc. |
| 22 | Distribution Lists (LOC, POC, General) |  |  | Tbd. |
| 23 | Inscriptions Fees | On the WEB site, through Indico; MCG to check with CP. Have to meet together and go through it. To ask for a TID for CERN Staff). Amount TBC Account to be created by Finance | MCG – CPP MCG check with MH LR + GG MCG Check with MH | In progress |